## PTR
Ambigai Project Tracking Report: ScaleNc
S. No. | Ambigai Project No. | Ambigai Project No. | Requestor Name | Customer Group | Operation | Type of Service | Scope | Number of Parts | Request Received date | ScaleNC Requested Delivery date | Estimation & Schedule Sent date | start date | Planned Delivery date | Modifed Planned Delivered Date | Actual Delivery date | Quoted time from ScaleNC | Actual Hours Spent | Week No | Billing month | Ambigai DUE/ DELIVERED Status | PORTAL DUE/ DELIVERED Status | Scope Tracking | Customer Feedback On Portal | Customer Feedback | IDC Engineer | Self QC | Peer QC
#REF! | ACS.ScaleNc.2023_1857 | ACS_#116239 | Sven Mai | Blechwerk Soest GmbH | 3d Model | CAD | To Create NC files. | 2 | 2023-07-31 | 2023-08-02 | 2023-08-02 | 2023-07-31 | 2023-08-02 |  | 2023-08-02 | NA | 1:00 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Jayakumar | Yes | Jayakumar
#REF! | ACS.ScaleNc.2023_1858 | ACS_#b17eb4 | jasmin roll | TRUMPF EaaS Reiff | Laser | CAM | To Create NC files. | 14 | 2023-07-31 | 2023-08-02 | 2023-08-02 | 2023-07-31 | 2023-08-02 |  | 2023-08-02 | NA | 4:45 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Jayaprakash | Yes | Jayakumar
#REF! | ACS.ScaleNc.2023_1859 | ACS_#d19688 | jasmin roll | Seeger Lasertechnik GmbH | 3d Model | CAD | To Create NC files. | 1 | 2023-07-31 | 2023-08-02 | 2023-08-02 | 2023-07-31 | 2023-08-02 |  | 2023-08-02 | NA | 0:30 | 31 | Aug_23 | Completed |  |  |  | ⚠Wrong pre Hole Diameter > See info in first order | Gnanamuthu | Yes | Dinesh
#REF! | ACS.ScaleNc.2023_1860 | ACS_#a88364 | jasmin roll | Seeger Lasertechnik GmbH | 3d Model | CAD | To Create NC files. | 13 | 2023-07-31 | 2023-08-02 | 2023-08-02 | 2023-07-31 | 2023-08-02 |  | 2023-08-02 | NA | 7:20 | 31 | Aug-23 | Completed |  |  |  | ⚠Wrong pre Hole Diameter > See info in first order | Dinesh | Yes | Gnanamuthu
#REF! | ACS.ScaleNc.2023_1861 | ACS_#8f018d | jasmin roll | Seeger Lasertechnik GmbH | 3d Model | CAD | To Create NC files. | 1 | 2023-07-31 | 2023-08-02 | 2023-08-02 | 2023-07-31 | 2023-08-02 |  | 2023-08-02 | NA | 0:15 | 31 | Aug | Completed |  |  |  |  | Dinesh | Yes | Gnanamuthu
#REF! | ACS.ScaleNc.2023_1862 | ACS_#86b7b0 | Arthur Milberger | POHL DWS | Punching | CAM | To Create NC files. | 18 | 2023-07-28 | 2023-08-01 | 2023-08-01 | 2023-07-28 | 2023-08-02 | 2023-08-02 | 2023-08-02 | NA | 1899-12-31 13:30 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Stephen | Yes | Hari
#REF! | ACS.ScaleNc.2023_1863 | ACS_#f68f0f | jasmin roll | TRUMPF EaaS Reiff | Laser | CAM | To Create NC files. | 17 | 2023-07-31 | 2023-08-02 | 2023-08-02 | 2023-07-31 | 2023-08-02 |  | 2023-08-02 | NA | 0.13889 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Jayaprakash | Yes | Jayakumar
#REF! | ACS.ScaleNc.2023_1864 | ACS_#21e8bc | jasmin roll | Lerch AG | Bending & Laser | CAM | To Create NC files. | 14 | 2023-07-31 | 2023-08-02 | 2023-08-02 | 2023-07-31 | 2023-08-02 |  | 2023-08-02 | NA | 0.1875 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Gnanamuthu& Jayakumar | Yes | Gnanamuthu
#REF! | ACS.ScaleNc.2023_1865 | ACS_#5053e0 | Arthur Milberger | Dobler-MBM GmbH | Punching | CAM | To Create NC files. | 101 | 2023-07-31 | 2023-08-02 | 2023-08-02 | 2023-07-31 | 2023-08-02 |  | 2023-08-02 | NA | 0.85417 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Stephen | Yes | Hari
#REF! | ACS.ScaleNc.2023_1866 | ACS_#5a7938 | Arthur Milberger | ABN | Punching & Laser | CAM | To Create NC files. | 1 | 2023-07-31 | 2023-08-02 | 2023-08-02 | 2023-07-31 | 2023-08-02 |  | 2023-08-02 | NA | 0.010417 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Manikanta | Yes | Hari
#REF! | ACS.ScaleNc.2023_1867 | ACS_#6384b1 | Arthur Milberger | ABN | Punching & Laser | CAM | To Create NC files. | 1 | 2023-07-31 | 2023-08-02 | 2023-08-02 | 2023-07-31 | 2023-08-02 |  | 2023-08-02 | NA | 0.027778 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Manikanta | Yes | Hari
#REF! | ACS.ScaleNc.2023_1868 | ACS_#00e59c | Arthur Milberger | ABN | Punching & Laser | CAM | To Create NC files. | 1 | 2023-07-31 | 2023-08-02 | 2023-08-02 | 2023-07-31 | 2023-08-02 |  | 2023-08-02 | NA | 0.027778 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Hari | Yes | Hari
#REF! | ACS.ScaleNc.2023_1869 | ACS_#213ab8 | Arthur Milberger | ABN | Punching & Laser | CAM | To Create NC files. | 1 | 2023-07-31 | 2023-08-02 | 2023-08-02 | 2023-07-31 | 2023-08-02 |  | 2023-08-02 | NA | 0.027778 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Hari | Yes | Hari
#REF! | ACS.ScaleNc.2023_1870 | ACS_#c14dcb | Sven Mai | Scholl Apparatebau GmbH & Co. KG | Punching & Laser | CAM | To Create NC files. | 7 | 2023-07-31 | 2023-08-02 | 2023-08-02 | 2023-07-31 | 2023-08-02 |  | 2023-08-02 | NA | 0.055556 | 31 | 8 | Completed |  |  |  | Feedback Please pay attention to the removal of the components that you do not drive over the sceleton where the components are already disposed of. | Jayaprakash | Yes | Jayakumar
#REF! | ACS.ScaleNc.2023_1871 | ACS_#4d5d31 | Arthur Milberger | Dobler-MBM GmbH | Punching | CAM | To Create NC files. | 145 | 2023-07-31 | 2023-08-02 | 2023-08-02 | 2023-07-31 | 2023-08-02 |  | 2023-08-02 | NA | 1900-01-01 01:30 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Stephen | Yes | Hari
#REF! | ACS.ScaleNc.2023_1872 | ACS_#c77f8c | jasmin roll | TRUMPF EaaS Gysi | Laser | CAM | To Create NC files. | 1 | 2023-07-31 | 2023-08-02 | 2023-08-02 | 2023-07-31 | 2023-08-02 |  | 2023-08-04 | NA | 0.020833 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Jayakumar | Yes | Jayakumar
#REF! | ACS.ScaleNc.2023_1873 | ACS_#d7a857 | jasmin roll | RecarO Aircraft Seating GmbH & Co. KG | bending | CAM | To Create NC files. | 2 | 2023-08-01 | 2023-08-03 | 2023-08-03 | 2023-08-02 | 2023-08-03 |  | 2023-08-03 | 0:25 | 0.16667 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Gnanamuthu | Yes | Gnanamuthu
#REF! | ACS.ScaleNc.2023_1874 | ACS_#03e7dd | jasmin roll | TRUMPF EaaS Gysi | Laser | CAM | To Create NC files. | 1 | 2023-08-02 | 2023-08-04 | 2023-08-03 | 2023-08-03 | 2023-08-03 |  | 2023-08-03 | NA | 0.020833 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Jayaprakash | Yes | Jayakumar
#REF! | ACS.ScaleNc.2023_1875 | ACS_#a81165 | jasmin roll | TRUMPF EaaS Reiff | Laser | CAM | To Create NC files. | 1 | 2023-08-02 | 2023-08-04 | 2023-08-03 | 2023-08-03 | 2023-08-03 |  | 2023-08-03 | NA | 0.024306 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Jayaprakash | Yes | Jayakumar
#REF! | ACS.ScaleNc.2023_1876 | ACS_#3b7606 | arthur Milberger | Dobler-MBM GmbH | Punching | CAM | To Create NC files. | 103 | 2023-08-02 | 2023-08-04 | 2023-08-04 | 2023-08-02 | 2023-08-04 |  | 2023-08-07 | NA | 1899-12-31 21:00 | 31 | 8 | Completed |  |  |  | Time | Stephen | Yes | Hari
#REF! | ACS.ScaleNc.2023_1877 | ACS_#daa2c2 | jasmin roll | TRUMPF EaaS Gysi | Laser | CAM | To Create NC files. | 2 | 2023-08-02 | 2023-08-04 | 2023-08-04 | 2023-08-02 | 2023-08-04 |  | 2023-08-04 | NA | 0.038194 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Jayaprakash | Yes | Jayakumar
#REF! | ACS.ScaleNc.2023_1878 | ACS_#9dac31 | Sven Mai | Scholl Apparatebau GmbH & Co. KG | Punching & Laser | CAM | To Create NC files. | 23 | 2023-08-02 | 2023-08-04 | 2023-08-04 | 2023-08-02 | 2023-08-04 |  | 2023-08-04 | NA | 0.33333 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Jayaprakash | Yes | Jayakumar
#REF! | ACS.ScaleNc.2023_1879 | ACS_#86da84 | Sven Mai | Scholl Apparatebau GmbH & Co. KG | Punching & Laser | CAM | To Create NC files. | 29 | 2023-08-01 | 2023-08-03 | 2023-08-03 | 2023-08-02 | 2023-08-03 |  | 2023-08-03 | NA | 0.40278 | 31 | 8 | Completed |  |  |  | Feedback For some parts ich changed the removal. Your result was over the flap an my result was to use the lift. Take a look to the setting for the palletizing it was not all the same. (Option how you place it down) | Jayaprakash | Yes | Jayakumar
#REF! | ACS.ScaleNc.2023_1880 | ACS_#8e8052 | Sven Mai | Schrag Fassaden | Punching & Laser | CAM | To Create NC files. | 39 | 2023-08-01 | 2023-08-04 | 2023-08-04 | 2023-08-02 | 2023-08-04 | 2023-08-09 | 2023-08-09 | NA | 1899-12-31 11:35 | 31 | 8 | Completed |  |  |  |  | Jayakumar & Jayaprakash | Yes | Jayakumar
#REF! | ACS.ScaleNc.2023_1881 | ACS_#a33002 | jasmin roll | Lerch AG | Bending & Laser | CAM | To Create NC files. | 17 | 2023-08-01 | 2023-08-04 | 2023-08-04 | 2023-08-02 | 2023-08-04 | 2023-08-07 | 2023-08-07 | NA | 0.36111 | 31 | 8 | Completed |  | Waiting for Customer Reply for One Bending Tool. So delivery date was modified. |  |  | Gnanamuthu& Jayakumar | Yes | Gnanamuthu
#REF! | ACS.ScaleNc.2023_1882 | ACS_#50413d | jasmin roll | TRUMPF EaaS Reiff | Laser | CAM | To Create NC files. | 1 | 2023-07-31 | 2023-08-01 | 2023-08-01 | 2023-08-01 | 2023-08-01 |  | 2023-08-01 | NA | 0.03125 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Jayakumar | Yes | Jayakumar
#REF! | ACS.ScaleNc.2023_1883 | ACS_#571b21 | jasmin roll | TRUMPF EaaS Reiff | Laser | CAM | To Create NC files. | 1 | 2023-07-31 | 2023-08-01 | 2023-08-01 | 2023-08-01 | 2023-08-01 |  | 2023-08-01 | NA | 0.038194 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Jayaprakash | Yes | Jayakumar
#REF! | ACS.ScaleNc.2023_M_083 | ACS_ScaleNc.2023_M_084 | Andreas Armbruster | Punching | Punching | CAM | Optimization & tool process |  | 2023-08-01 |  |  | 2023-08-01 |  |  | 2023-08-01 | 0.11111 | 0.11111 | 31 | 8 | Completed |  |  |  |  | Ambigai Team |  | Ambigai Team
#REF! | ACS.ScaleNc.2023_M_084 | ACS_ScaleNc.2023_M_085 | Andreas Armbruster & Arthur | Runa GmbH | Punching | CAM | Countersink tool -Processing sample |  | 2023-08-03 |  |  | 2023-08-03 |  |  | 2023-08-03 | 0.22222 | 0.22222 | 31 | 8 | Completed |  |  |  |  | Ambigai Team |  | Ambigai Team
#REF! | ACS.ScaleNc.2023_M_085 | ACS_ScaleNc.2023_M_083 | Armbruster,Arthur,Sven |  |  | Team Meeting | Team meeting: CW-29 To share current week Jobs status and Feedback. |  | 2023-08-03 |  |  | 2023-08-03 |  |  | 2023-08-03 | 0.11111 | 0.11111 | 31 | 8 | Completed |  |  |  |  | Ambigai Team |  | Ambigai Team
#REF! | ACS.ScaleNc.2023_1884 | ACS_ScaleNc.2023_M_084 | Sven Mai | Faiveley Transport Leipzig GmbH & Co KG | Punching | CAM | To Create NC files. | 177 | 2023-08-03 | 2023-08-09 | 2023-08-09 | 2023-08-03 | 2023-08-09 |  | 2023-08-09 | NA | 1900-01-05 04:00 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Hari,Sivakumar | Yes | Hari
#REF! | ACS.ScaleNc.2023_1885 | ACS_ScaleNc.2023_M_085 | arthur Milberger | Alpha Verteilertechnik GmbH | Punching | CAM | To Create NC files. | 5 | 2023-08-02 | 2023-08-05 | 2023-08-05 | 2023-08-03 | 2023-08-05 |  | 2023-08-07 | NA | 0.27083 | 31 | Aug_23 | Completed |  |  |  | Customer Feedback: Green | sribalaji | Yes | Hari
#REF! | ACS.ScaleNc.2023_1886 | ACS_ScaleNc.2023_M_086 | arthur Milberger | Alpha Verteilertechnik GmbH | Punching | CAM | To Create NC files. | 6 | 2023-08-02 | 2023-08-05 | 2023-08-05 | 2023-08-03 | 2023-08-05 |  | 2023-08-04 | NA | 0.16667 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | sribalaji | Yes | Hari
#REF! | ACS.ScaleNc.2023_1887 | ACS_ScaleNc.2023_M_087 | arthur Milberger | Alpha Verteilertechnik GmbH | Punching | CAM | To Create NC files. | 8 | 2023-08-02 | 2023-08-05 | 2023-08-05 | 2023-08-03 | 2023-08-05 |  | 2023-08-04 | NA | 0.14583 | 31 | Aug-23 | Completed |  |  |  | Customer Feedback: Green | sribalaji | Yes | Hari
#REF! | ACS.ScaleNc.2023_1888 | ACS_ScaleNc.2023_M_088 | jasmin roll | TRUMPF EaaS Reiff | Laser | CAM | To Create NC files. | 1 | 2023-08-03 | 2023-08-05 | 2023-08-04 | 2023-08-04 | 2023-08-04 |  | 2023-08-04 | NA | 0.020833 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Jayaprakash | Yes | Jayakumar
#REF! | ACS.ScaleNc.2023_1889 | ACS_ScaleNc.2023_M_089 | arthur Milberger | Alpha Verteilertechnik GmbH | Punching | CAM | To Create NC files. | 10 | 2023-08-04 | 2023-08-08 | 2023-08-08 | 2023-08-04 | 2023-08-08 |  | 2023-08-07 | NA | 0.20833 | 31 | 8 | Completed |  |  |  | Time | Hari | Yes | Hari
#REF! | ACS.ScaleNc.2023_1890 | ACS_ScaleNc.2023_M_090 | arthur Milberger | Alpha Verteilertechnik GmbH | Punching | CAM | To Create NC files. | 9 | 2023-08-04 | 2023-08-08 | 2023-08-08 | 2023-08-04 | 2023-08-08 |  | 2023-08-07 | NA | 0.1875 | 31 | Aug | Completed |  |  |  | Time | Hari | Yes | Hari
#REF! | ACS.ScaleNc.2023_1891 | ACS_ScaleNc.2023_M_091 | arthur Milberger | Alpha Verteilertechnik GmbH | Punching | CAM | To Create NC files. | 6 | 2023-08-04 | 2023-08-08 | 2023-08-08 | 2023-08-04 | 2023-08-08 |  | 2023-08-07 | NA | 0.1875 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Hari | Yes | Hari
#REF! | ACS.ScaleNc.2023_1892 | ACS_ScaleNc.2023_M_092 | arthur Milberger | Alpha Verteilertechnik GmbH | Punching | CAM | To Create NC files. | 14 | 2023-08-04 | 2023-08-08 | 2023-08-08 | 2023-08-04 | 2023-08-08 |  | 2023-08-07 | NA | 0.34375 | 31 | 8 | Completed |  |  |  | Time | Hari | Yes | Hari
#REF! | ACS.ScaleNc.2023_1893 | ACS_ScaleNc.2023_M_093 | jasmin roll | Schrag Fassaden | Punching & Laser | CAM | To Create NC files. | 104 | 2023-08-04 | 2023-08-11 | 2023-08-11 | 2023-08-07 | 2023-08-11 |  | 2023-08-11 | NA | 1899-12-31 19:00 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Dinesh, Gnanamuthu, Jayakumar | Yes | Jayakumar
#REF! | ACS.ScaleNc.2023_1894 | ACS_ScaleNc.2023_M_094 | jasmin roll | TRUMPF EaaS Gysi | Laser | CAM | To Create NC files. | 5 | 2023-08-04 | 2023-08-08 | 2023-08-08 | 2023-08-04 | 2023-08-08 |  | 2023-08-07 | NA | 0.12153 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Jayakumar | Yes | Jayakumar
#REF! | ACS.ScaleNc.2023_1895 | ACS_ScaleNc.2023_M_095 | jasmin roll | TRUMPF EaaS Gysi | Laser | CAM | To Create NC files. | 2 | 2023-08-04 | 2023-08-08 | 2023-08-08 | 2023-08-04 | 2023-08-08 |  | 2023-08-07 | NA | 0.03125 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Jayakumar | Yes | Jayakumar
#REF! | ACS.ScaleNc.2023_139 | ACS_ScaleNc.2023_M_096 | Sven Mai | Scholl Apparatebau GmbH & Co. KG | Documentation | CAM | Guideline Updated |  | 2023-08-04 |  |  | 2023-08-04 |  |  | 2023-08-04 | 2:00 | 0.083333 | 31 | 8 | Completed |  |  |  | Customer Feedback: Green | Jayaprakash |  | Jayakumar
#REF! | ACS.ScaleNc.2023_M_086 | ACS_ScaleNc.2023_M_086 | Andreas Armbruster | CAD | CAD | CAD | Standard Design Guidelines reviewed. |  | 2023-08-07 |  |  | 2023-08-07 |  |  | 2023-08-07 | NA | 0.11111 | 32 | 8 | Completed |  |  |  |  | Ambigai Team |  | Ambigai Team
#REF! | ACS.ScaleNc.2023_M_087 | ACS_ScaleNc.2023_M_087 | Andreas Armbruster | Recaro | Bending | CAM | Strategy for Mirror Parts | 1 | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-08-09 |  | 2023-08-09 | NA | 0.090278 | 32 | 8 | Completed |  |  |  |  | Ambigai Team |  | Ambigai Team
#REF! | ACS.ScaleNc.2023_M_088 | ACS_ScaleNc.2023_M_088 | Andreas Armbruster & Arthur | Discussion about Done jobs and Current jobs |  | CAM |  |  | 2023-08-10 | 2023-08-10 | 2023-08-10 | 2023-08-10 | 2023-08-10 |  | 2023-08-10 | NA | 0.14583 | 32 | 8 | Completed |  |  |  |  | Ambigai Team |  | Ambigai Team
#REF! | ACS.ScaleNc.2023_M_089 | ACS_ScaleNc.2023_M_089 | jasmin roll | Clamping Procedure - Detailed Explanation | Laser | CAM |  |  | 2023-08-10 | 2023-08-10 | 2023-08-10 | 2023-08-10 | 2023-08-10 |  | 2023-08-10 | NA | 0.097222 | 32 | 8 | Completed |  |  |  |  | Ambigai Team |  | Ambigai Team
#REF! | ACS.ScaleNc.2023_M_090 | ACS_ScaleNc.2023_M_090 | Andreas Armbruster & Arthur | Discussion about Current jobs - 3d Model Creation | Punching | CAM |  |  | 2023-08-10 | 2023-08-10 | 2023-08-10 | 2023-08-10 | 2023-08-10 |  | 2023-08-10 | NA | 0.097222 | 32 | 8 | Completed |  |  |  |  | Ambigai Team |  | Ambigai Team
#REF! | ACS.ScaleNc.2023_M_091 | ACS_ScaleNc.2023_M_091 | Andreas Armbruster & Arthur | Discussion about Done jobs and Current jobs |  |  |  |  | 2023-08-18 | 2023-08-18 | 2023-08-18 | 2023-08-18 | 2023-08-18 |  | 2023-08-18 | NA | 0.14583 | 33 | 8 | Completed |  |  |  |  | Ambigai Team | Yes | Ambigai Team
#REF! | ACS.ScaleNc.2023_M_092 | ACS_ScaleNc.2023_M_092 | Andreas Armbruster & Arthur | Discussion about Dobler and Bend Line and Recaro Current Jobs | Punching | CAM |  |  | 2023-08-18 | 2023-08-18 | 2023-08-18 | 2023-08-18 | 2023-08-18 |  | 2023-08-18 | NA | 0.097222 | 33 | 8 | Completed |  |  |  |  | Ambigai Team | Yes | Ambigai Team
#REF! | ACS.ScaleNc.2023_M_093 | ACS_ScaleNc.2023_M_093 | Andreas Armbruster & Arthur |  | CAD | CAD |  |  | 2023-08-21 |  |  | 2023-08-21 |  |  | 2023-08-21 | 0.1875 | 0.1875 | 34 | 8 | Completed | [5 empty] | Yes
#REF! | ACS.ScaleNc.2023_M_094 | ACS_ScaleNc.2023_M_094 | Andreas Armbruster & Arthur | Alpha Verteilertechnik GmbH | Punching | CAM | Tooling process |  | 2023-08-22 |  |  | 2023-08-22 |  |  | 2023-08-22 | 0.076389 | 0.076389 | 34 | 8 | Completed | [5 empty] | Yes
#REF! | ACS.ScaleNc.2023_M_095 | ACS_ScaleNc.2023_M_095 | Andreas Armbruster & Arthur | Discussion about Done jobs and Current jobs |  |  |  |  | 2023-08-25 |  |  | 2023-08-25 |  |  | 2023-08-25 | 0.09375 | 0.09375 | 34 | 8 | Completed | [5 empty] | Yes
#REF! | ACS.ScaleNc.2023_M_096 | ACS_ScaleNc.2023_M_096 | jasmin roll | LST Laser & Schalttechnik GmbH & Co.KG | Documentation | CAM | meeting |  | 2023-08-25 |  |  | 2023-08-25 |  |  | 2023-08-25 | 0.010417 | 0.010417 | 34 | 8 | Completed | [5 empty] | Yes
Note on Z2: - Input Study - To respond in PORTal for the job order - Resposible for Portal communication - Check the PTR Document (for start date, inputs, Input change details, Start date, Delivery date change…) - Will share the Inputs, guide lines to follow to Peer person - Will share the learning points to the team and requet Design Guide line document controller to update the guidel lines document - Will get the feedback received from requester and from Customer End
Note on AA2: - Input Study - Resposible for Portal communication - Resposible for PTR data updates (for start date, inputs, Input change details, Start date, Delivery date change…) - Will share the Inputs, guide lines to follow to Peer C person - Will share the learning points to the team and requet Design Guide line document controller to update the guidel lines document - Will get the feedback received from requester and from Customer End
Note on AB2: - Get Input summary from the executer before executer starts work - Intermediate reviews with executer - Needs to get for any additional input/input chnages - Will update the remarks/OK in PTR internal obervations for each part/each program w.r.t inputs/additional inputs - Will get the learning points from the executor and check the Design guide line documents i uodate as upto date - Will get the feedback received from requester and from Customer End